## Intial Schedule
| Estimated Date | Notes
Languages:
Production
Concept Phase Completed | 2012-07-26
Requirements Phase Completed | 2012-08-15
Initial Game Plan Completed | 2012-07-24
First Playable | 2012-08-22
Alpha | 2012-09-11
Beta | 2012-09-28
Approvals
Concept Approval | 2012-07-27
Requirements Approval | 2012-08-16
Game Plan Approval | 2012-07-25
Design
Deliverables Completed for Concept Phase | 2012-07-28
Deliverables Completed for Requirements Phase | 2012-08-17
Detailed Documentation Completed for Game Features | 2012-08-15
Character and Story Documents Completed | 2012-08-11
Mission and Scenarios Designed | 2012-07-25
Mission Prototypes Scripted | 2012-07-18
Playtesting | 2012-09-28
Final Missions Scripted | 2012-08-15
Art
Deliverables Completed for Concept Phase | 2012-08-15
Deliverables Completed for Requirements Phase | 2012-08-16
Prototypes Completed | 2012-08-01
First Playable Level Completed | 2012-08-22
Special Effects Completed | 2012-09-27
UI Completed | 2012-08-29
Cinematics Completed | N/A
Engineering
Deliverables Completed for Concept Phase | 2012-08-15
Deliverables Completed for Requirements Phase | 2012-08-16
Production Pipeline Completed | 2012-09-10
Engineering Prototypes Completed | 2012-09-17
All Major Game Play Features Implemented | 2012-09-28
Audio
Audio Files Acquired/Completed | 2012-08-01
Audio Placeholders Implemented | 2012-09-11
Final Audio Implemented | 2012-09-28
Final Music Implemented in Game | 2012-09-28
QA
Test Plan Completed | 2012-08-22
First Playable Testing Completed | 2012-08-22
Alpha Testing Completed | 2012-09-11
Playtesting Completed | 2012-09-28
Marketing
Demo Build | 2012-10-12